## TGIF Conference Cost Worksheet
WBS | Name | Duration (Days) | Work (Hours) | Cost ($s) | Note | Personel | $
1 | TGIF AI Conference | 102 | 1012 | 106423.4697 | 3 days conference with about 100 attendee | Project Manager | 75/hour
1.1 | Planning | 17 | 200 | 11408.3534 |  | PMO Staff | 35/hour
1.1.1 | Agenda/Content | 6 | 48 | 3001.4963 | Project Manager[69%];PMO Staff[31%] | Operations Manager | 40/hour
1.1.2 | Location Selection | 3 | 36 | 1860 | Project Manager[50%];Operations Manager | Operations Officer | 25/hour
1.1.3 | Speaker Strategy | 2 | 16 | 614.8571 | Project Manager[69%];PMO Staff[91%] | Music operator | 30/hour
1.1.4 | Attendee Strategy | 2 | 16 | 752 | Project Manager[60%];PMO Staff[70%] | Lighting operator | 30/hour
1.1.5 | Vendors/Sponsors | 7 | 84 | 5180 | Project Manager;PMO Staff[50%] | On-Site Help | 20/hour
1.2 | Content (Speakers/Experts) | 17 | 152 | 5960 |  | Cleaning staff | 20/hour
1.2.1 | Identifying | 10 | 120 | 4200
1.2.1.1 | Academia | 10 | 40 | 1400 | PMO Staff[50%]
1.2.1.2 | Industry | 10 | 40 | 1400 | PMO Staff[50%]
1.2.1.3 | Public Sector | 10 | 40 | 1400 | PMO Staff[50%]
1.2.2 | Confirming | 7 | 32 | 1760 | Project Manager[29%];PMO Staff[29%]
1.3 | Partnerships/Procurement | 5 | 40 | 2200
1.3.1 | Tech companies | 5 | 20 | 1100 | Project Manager[25%];PMO Staff[25%]
1.3.2 | AI Vendors | 5 | 20 | 1100 | Project Manager[25%];PMO Staff[25%]
1.4 | Attendee Management | 27 | 66 | 1650
1.4.1 | Guest List | 2 | 16 | 400 | Operations Officer
1.4.2 | RSVPs | 20 | 25 | 625 | Operations Officer[16%]
1.4.3 | Handouts | 5 | 10 | 250 | Operations Officer[25%]
1.4.4 | Special Needs | 3 | 15 | 375 | Operations Officer[62%]
1.5 | Marketing/Communications | 50 | 0 | 14215.1163 | Outsource
1.5.1 | Physical | 43 | 0 | 1715.1163 | Marketing
1.5.2 | Onliine | 20 | 0 | 2500 | Marketing
1.5.3 | PR | 30 | 0 | 2500 | Marketing
1.5.4 | Press/Media | 6 | 0 | 2500 | Marketing
1.5.5 | Merchandise | 10 | 0 | 2500 | Marketing
1.5.6 | Feedback/Sales Analysis | 7 | 0 | 2500 | Marketing
1.6 | Conference Operations | 8 | 62 | 45860
1.6.1 | Venue | 8 | 56 | 44700
1.6.1.1 | Booking | 1 | 8 | 200 | Operations Officer
1.6.1.2 | Rooms and Equipment | 3 | 0 | 7500 | Rooms And Equipment | Renting fee
1.6.1.3 | Tables/Chairs | 3 | 0 | 1500 | Tables/Chairs | Renting fee
1.6.1.4 | Decorations | 1 | 0 | 500 | Decoration | Bought from Amazon
1.6.1.5 | Music | 3 | 24 | 720 | Music operator
1.6.1.6 | Lighting | 3 | 24 | 720 | Lighting operator
1.6.1.7 | Furnishing | 3 | 0 | 300 | Furnishing | Renting fee
1.6.1.8 | Signage | 2 | 0 | 260 | Signage | Bought from Amazon
1.6.1.9 | Food and Beverage | 3 | 0 | 33000 | Food and Beverages | (15(Breakfast )+25(Lunch)+10(Snacks) +15(Baverage )))*3+40(Dinner)*2)*100
1.6.2 | Security | 2 | 6 | 240 | Operations Manager[38%]
1.6.3 | Technology | 3 | 0 | 920
1.6.3.1 | Live Streaming | 3 | 0 | 460 | Photography[0.2]
1.6.3.2 | Audio/Visual | 3 | 0 | 460 | Photography[0.2]
1.7 | Administration | 65 | 468 | 24080
1.7.1 | Staffing (Volutneers/Workers) | 14 | 98 | 8580
1.7.1.1 | Ticketing | 5 | 20 | 400 | On-Site Help[50%]
1.7.1.2 | Security | 3 | 0 | 1920 | Security
1.7.1.3 | Tables Set Up | 3 | 6 | 120 | On-Site Help[25%]
1.7.1.4 | MC/Hosts | 3 | 0 | 1800 | MC/Hosts
1.7.1.5 | Photography | 3 | 0 | 1380 | Photography[0.6]
1.7.1.6 | Caterers | 3 | 0 | 2000 | Catering Team
1.7.1.7 | Cleaning Staff | 3 | 24 | 480 | Cleaning staff
1.7.1.8 | Breakdown | 3 | 24 | 480 | On-Site Help
1.7.2 | Budget | 65 | 370 | 15500
1.7.2.1 | Revenue | 22.5 | 240 | 9000
1.7.2.1.1 | Ticket MGMT | 12.5 | 200 | 7500 | Operations Manager;PMO Staff
1.7.2.1.2 | Sponsor MGMT | 10 | 40 | 1500 | PMO Staff[25%];Operations Manager[25%]
1.7.2.2 | Expenses | 65 | 130 | 6500 | Project Manager[8%];PMO Staff[8%];Operations Manager[8%]
1.8 | Project Close-Out | 3 | 24 | 1050 | Project Manager[25%];PMO Staff[25%];Operations Manager[25%];Operations Officer[25%]